Project Completion Review - Top Sheet

Review Date:	07/12/2016

Title: Norwegian Refugee Council (NRC): Legal assistance to prevent demolitions and displacement in the Occupied Palestinian Territories (OPTs).
Programme Code: / 202443	Start Date: / 1st April 2013	End Date: / 30th September 2016
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance
Year	2013/14	2014/15	2015/16	2016/17
Programme Score	A	A+	A+	A+
Risk Rating	Medium	Medium	Moderate	Moderate

Financial Position
Original Programme Value	£3m
Extensions/ amendments	Cost Extension for Scale up in June, 2014 for £0.5m. / Cost extension for Bridge Funding in January 2015 for £2m. / Cost extension for Bridge Funding in March, 2016 for £1m.
Log-frame revisions (with dates)	Log frame created in February 2013 / Revision 1: July, 2014. / Revision 2: June, 2015. / Revision 3: August, 2016.
Total programme spend	£6,493,173.86

Headline Information on the Programme
The UK has provided £6.49 million over four years to deliver legal aid to defend the Housing, Land and Property (HLP) rights of Palestinians in Area C, and Gaza. This support was delivered through the Norwegian Refugee Council’s (NRC) Information, Counselling, and Legal Assistance (ICLA) Programme. The programme has been operating in the OPTs since 2010 and has established partnerships with several Israeli and Palestinian NGOs and private lawyers. ICLA’s main objective is to prevent forced displacement by providing legal information, counselling and/or assistance to people who have already been displaced or are at risk of displacement.

The legal assistance is provided by NGO partners and private lawyers. NRC staff in the West Bank and Gaza provide counselling, information and referrals and follow up on cases and issues with providers and national and international stakeholders. NRC staff and partners work together to provide evidence and analysis which forms the basis of their research, advocacy and support to the Palestinian Authority.

Despite the increasingly challenging context and increase in demolition activity the programme has continued to help prevent demolitions and displacement in the OPTs and the results of this programme have contributed to the following DFID OPTs 2011-2015 Departmental Results Framework (DRF) indicators:

- 2,639 eviction or demolition orders (out of a total 2,690 cases) suspended as a result of DFID-supported interventions; and
- Over 21,500 people have been supported through the programme from 2013 to 2016 including 13,291 individuals provided with information, advice and legal assistance services; and 8,281 individuals supported to improve their rights to land and property.

Moreover, 96.6% of households in Area C who received legal representation provided through NRC were able to receive a temporary suspension of demolition order due that legal representation. The programme also exposed a total of 152 policies and practices through public interest cases.

Context
Demolitions, evictions, forcible relocation and displacement threaten the viability of the two-state solution. The systematic violation of the HLP rights of Palestinians and consequent population displacement are further reducing Palestinian presence in Area C and East Jerusalem and damaging the prospects of a future, geographically contiguous, and viable Palestinian state. HLP violations affect livelihood structures, reduce sources of income and lower living standards. Demolitions also increase dependency on humanitarian assistance and have a range of negative psycho-social impacts, particularly on children.

The demolition of Palestinian homes and livelihoods structures on the basis of a lack of Israeli building permits in the West Bank, including Area C and East Jerusalem, places households and entire communities at risk of forcible transfer. Between January and November 2016 there has been a sharp increase in the number of demolitions: a total of 1,051 Palestinian-owned structures have been demolished; whereas the total number of structures demolished in 2015 was 544.[1] In September and October of 2016 the Israeli authorities confiscated, demolished, or forced Palestinians to demolish, 155 structures across the West Bank, displacing some 240 people, half of them children, and otherwise affecting more than 350 people. All but two of these incidents took place on the grounds that no Israeli-issued building permits had been issued, with 94%[2] rejection rate. Since the beginning of 2016 the demolition rate has been over 80 per cent higher than in 2015, and the highest since UN/OCHA began recording demolitions in 2009.
[1] Protection of Civilians Weekly Report 15-28 November, 2016. <http://www.ochaopt.org/content/protection-civilians-weekly-report-15-28-november-2016>
[2] < https://www.map-uk.org/downloads/reports/Failing-to-make-the-grade.pdf>

Lack of political progress in the Peace Process has meant that Israel continues to implement a planning regime in Area C and East Jerusalem that is contrary to international humanitarian law. Palestinians in Area C are governed not by Israeli domestic law but by a combination of Ottoman, British and Jordanian law amended by more than 1,600 Israeli military orders. In Area C and East Jerusalem, legal cases often take years and the costs are very high. Consequently, Palestinians have very little access to justice and, for many, accessing legal aid is the only way to defend their housing, land and property rights.

In Gaza, there was continued need for HLP support to facilitate reconstruction after the 2014 conflict. A large number of Gazans were displaced by the conflict, and still more required assistance to rebuild and repair damaged houses. Legal support is required to obtain property documentation, building permits and reconstruction grants.

Addressing these issues through legal assistance is not always suitable, particularly in East Jerusalem and Area C. However, where it is suitable, a lack of legal representation could result in an increased number of people being displaced, or having their homes demolished. by providing free legal counselling and representation for Palestinians facing violations to HLP rights in This would lead to increased poverty, increased reliance on aid, reduced access to health and education services and negative psychosocial effects. This programme was able to address the need to improve access to justice the West Bank and Gaza. Overall, where a legal response was suitable, the programme was very successful in responding to the deteriorating operating environment and has overachieved against output and outcome milestones.

Follow up actions required following closure
Following project closure, the following actions will be required:

1. Sharing the PCR with NRC for comments and suggestions.
2. Declaring the PCR as record in order for it to be published on Development Tracker.
3. Informing NRC of project closure procedures, including completing the assets transfer procedures.
4. DFID will continue to be engaged with ongoing legal aid, which will be managed by FCO, to support our political messaging and diplomatic activity.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202443/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202443/documents

Outline of programme and what it has achieved
The project completion review (PCR) covers DFID funding to the Norwegian Refugee Council’s (NRC’s) Information, Counselling and Legal Assistance (ICLA) programme between 1 April, 2013 – 30 September 2016. The last Annual Review was conducted in April 2016, concluding that NRC had exceeded expectations against results. This PCR will highlight major programme achievements since 2013. Description of outputs will highlight progress against milestones reflecting the period from 1 April – 30 September 2016, which was not covered in previous Annual Reviews. Overall, where a legal response was suitable, the programme was very successful in responding to the deteriorating operating environment and has overachieved against output and outcome milestones. The programme was able to support a large number of households to receive a temporary suspension of demolition order through the provision of legal aid and representation, partly mitigating the overall rise in demolitions.

Programme objectives
- Palestinian housing, land, property (HLP) rights are protected
- Beneficiaries are empowered and the capacity of lawyers and other humanitarian professionals on housing, land, property rights is enhanced
- Policies and practices causing displacement are highlighted, challenged and ultimately changed

Outcome indicators
- % of households in Area C who have eviction or demolition orders and remain in their homes due to legal representation provided through NRC.
- % of beneficiaries participating in information sessions who report the information presented will assist them in their daily lives (sex-disaggregated)
- # of incidences where power holders act positively on information received from NRC in an effort to reduce forced displacement.
- % of women surveyed in households receiving legal representation and counselling who report involvement in their case. (West Bank – public interest cases, Gaza-beneficiaries of legal counselling).

NRC has been able to respond to increased demand for the ICLA programme while still maintaining a high quality of delivery. Key Programme Achievements include:
- Programme beneficiaries have become better informed about their rights and about the programme’s representation services, as the programme supported beneficiaries who required a lawyer to help them challenge a demolition/eviction order and other rights violations rather than those who require one-off legal counselling.
- The programme introduced Mobile Legal Clinics in remote parts of Gaza which facilitated access to legal services for a large number of beneficiaries who could not otherwise access the NRC Gaza office.
- The programme made good progress on strengthening its gender focus; the programme was able to support women improve access to their HLP rights in light of the reconstruction process of the Gaza Strip.
- The programme made good progress on improving the accessibility through NRC’s website to briefing and advocacy materials including developing materials which are more user-friendly.
- The programme was able to build a constructive and effective cooperation with the Palestinian Authority (PA) and strengthen this coordination through the provision of technical assistance and training events.
- The programme has exposed or challenged a range of laws, policies or practices that beneficiaries and other stakeholders consider either discriminatory and/or possible to legally challenge through public interest cases, including:
  - Seizure of properties in the Old City of Hebron;
  - Displacement of Palestinian residents.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
The outcome of this programme is that Palestinians at risk of displacement within the OPTs are better able to uphold their HLP rights through provision of legal aid services and increased access to justice. NRC has moderately exceeded expectation on outcome-level targets throughout the programme, substantially exceeding three targets. Only one target was slightly underachieved during one year.

Over the last reporting period (1 April 2016 – 30 September 2016), NRC substantially exceeded all outcome-level targets. The table below captures outcome indicators’ progress against milestones since the beginning of the programme:

Outcome Indicators		2014	2015	2016[3]
	Milestone	95%	95%	95%
1. Percentage of households in Area C who receive a temporary suspension of demolition order due to legal representation provided through NRC.	Progress	97%	95%	98%
2. Percentage of beneficiaries participating in information sessions who report the information presented will assist them in their daily lives (sex disaggregated).	Milestone	70%	80%	80%
	Progress	80%[4]	86%[5]	95%
3. Number of incidences where power holders act positively on information received from NRC in an effort to reduce forced displacement.	Milestone	5	17	8
	Progress	10	17	25
4. Percentage of beneficiaries who obtain residency permit or other registration as a result of NRC services.	Milestone	0	50%	40%
	Progress	0	98%	72%
5. Percentage of women surveyed in households receiving legal representation and counselling who report sufficient knowledge of their case.	Milestone	60%	80%	50%
	Progress	70%	73%	68%
[3] 2016 results are based in the weighted average covering the period from 1 April 2015 – 30 September 2016.
[4] West Bank: 79% males and 73% females. Gaza: 87% males and 84% females.
[5] West Bank: 78% males and 81% females. Gaza: 91% males and 92% females.

The overall outcome score for the period between 1 April 2016 – 30 September 2016 is A+, as outcomes moderately exceeded expectation. This follows scores of A, A+ and A+ in the previous 3 annual reviews.

Throughout the life of the programme NRC met expectations and moderately exceeded expectations with the exception outcome indicator 5 duing 2015.

NRC enabled 96.6% of beneficiaries to remain in their homes in Area C after receiving eviction/demolition orders, through the provision of legal support. NRC's advocacy strategy for Gaza focused on facilitating reconstruction, wherein HLP rights form a key component. To this end, NRC has undertaken a number of meetings with diplomats and other decision makers locally, as well as holding regular briefings in the EU to emphasise the importance of support for HLP rights in reconstruction.

Beneficiaries provided positive feedback with 95% (during the last six month) of beneficiaries participating in information sessions reported that the information presented will assist them in their daily lives. Moreover, there was a 72% success rate of beneficiaries who were able to obtain residency permits and/or other registration as a result of NRC Services.

As part of its ‘policy change’ response, the NRC ICLA programme has undertaken a number of public interest cases for Palestinian communities in the West Bank (Area C) as well as in the Gaza Strip. Public interest cases are defined as all community cases, test cases, class action cases and public interest cases which either, change, challenge or expose an unjust law, policy or practice. Such cases have the potential to affect large numbers of Palestinians through a positive court judgment, which changes an unfair policy. Sometimes the lodging of a public interest case in itself can temporarily halt an unfair practice affecting a large number of persons (indirect beneficiaries) until the court has resolved the issue. Public interest cases can be complex, lengthy and can result in negative or positive precedents. With the support of DFID; ICLA supported 152 public interest cases in Area C of the West Bank through implementing partners or private lawyers.

Output Score and Description

The overall output score for the period 1 April 2016 – 30 September 2016 is A+, output targets have moderately exceeded expectation for the last six months.

Output number	Output Description	Impact Weight (%)	Output Performance	Risk
1	Emergency Legal Response: Provision of emergency legal counselling and representation to Palestinians at risk of displacement in Area C, and Gaza.	30%	A	Minor
2	Preventative Legal Response: A longer term legal strategy that helps to prevent demolitions and displacement	30%	A+	Minor
3	Policy Change Response: Influencing policy change on HLP and residency rights violations through advocacy.	30%	A+	Minor
4	PA Capacity Building Response: Strengthen the capacity of the PA to provide legal aid in HLP cases.	10%	A++	Minor

The scoring for the last six months is consistent with the scoring in previous periods. Therefore we use this scoring as final output score for the project’s performance over four years. See Annex 1 for details of all results achieved over 2013 to 2016.

Lessons and how these have been shared

The programme was able to meet and in some cases overachieve all target output and outcome indicators not only for the past six months, but also since the beginning of the programme in 2013, with the exception of one outcome indicator during one year. However, due to the nature and complexity of public interest cases, many cases are still pending court hearings; other eviction proceedings remain stuck at various stages in the Israeli court system, whereas there are appeal cases which were dismissed or refused by court and therefore cases were closed. In future programmes, NRC should explore further engagement with missions based in Jerusalem, Ramallah and Tel Aviv to assess how their advocacy materials are being used by the international community and shape their future advocacy strategy given the increase in demolitions, eviction orders, and forcible transfers.

DFID’s support to legal aid in the OPTs will be transitioned to and managed in future by the FCO. DFID and the FCO (based in Jerusalem and Tel Aviv) have worked closely together to ensure a smooth transition in order to link programmatic support for legal aid with our political messaging and diplomatic activity.

The impact that we aim to achieve through this project is a reduction in the number of demolitions. Despite the success of this programme there has been an increase in the overall number of demolitions. In the absence of this programme the number of demolitions would be even higher. So the programme is having an impact but we must recognise that the programme is only helpful for those people who legal aid can support. There are many people for whom the programme (as currently operated) cannot assist. Future phases should consider whether the programme could be re-designed to have a broader impact.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Emergency Legal Response- Provision of emergency legal counselling and representation to Palestinians at risk of displacement in Area C and Gaza.
Output number per LF		1	Output Score (for period 1 April 2016 – 30 September 2016)	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones / Six months to September, 2016	Progress / Six months toSeptember, 2016	Total Target	Total Achieved
1.1	# Of male and female beneficiaries receiving legal counselling on HLP and residency issues.	Total 350 comprising: / West Bank: 200 (HLP) / Gaza: 150 (HLP)	Total 496 comprising: / West Bank: 172 (139m/33f) HLP / Gaza: 324 (170m/80f/74 children)	Total: 7,495 / - West Bank: 4,880 / - Gaza Strip: 2,615	Total: 7,648 / - West Bank: 4,980 / - Gaza Strip: 2,668
	# Of opened and ongoing cases of legal assistance.	Total 1,539 comprising: / - 100 new / - 1,439 ongoing	Total 1,734 comprising: / - 252 new / - 1,482 ongoing	Total 3,559 Comprising: / - 1,200 New / - 2,359 Ongoing	Total 4,015 / Comprising: / - 1,656 New / - 2,359 ongoing
1.3	# of Palestinian women displaced during operation Protective Edge in Gaza who receive legal counselling and/or representation from NRC or NRC partners	50 women	40 women[6]	900	595
[6] This target was slightly under-achieved, because of negative soceital norms. In Palestine, men are the usual owners of houses/property in Gaza, and as the HLP caseload focuses on completing the chain of ownership, so as to help families receive reconstruction grants, NRC naturally engaged more men than women.

Key Points
Output Indicator 1.1 Counselling: During the final six months reporting period, NRC has responded to a high level of need for legal counselling, exceeding the overall target by 51%, bringing the total number of people counselled to 7,648 male and female beneficiaries. Counselling sessions on Housing, Land and Property rights were more likely to result in the need for legal representation in court. Additionally 150 individuals were provided with legal counselling, to obtain permits to leave Gaza for residency and other related issues.

Output Indicator 1.2 Legal Assistance: Through its partners and contracted private lawyers, NRC coordinated legal representation for a large number of cases and have overachieved the target during the six month reporting period by 12% bringing the total number of opened and ongoing legal cases to 4,015. This exceed the target by 456 cases, a significant achievement. In Gaza, the programme provided legal assistance to households on HLP to assist them with completing their chain of ownership to protect their security of tenure and ensure their efforts to benefit from reconstruction grants are not hindered by the lack of proper documentation.

Output Indicator 1.3 Legal Support for Women: The programme sustained its approach to prioritising displaced women to improve their HLP rights. During the last 6 months of the programme, NRC supported 40 women displaced due to the 2014 conflict by assisting them to obtain the necessary ownership documents, to enhance their security of tenure. This was under achievement on the target by 20% (see footnote below). Overall, the set target was underachieved by 33%, which is mainly due to overestimating the target during the first year of the project. It is important to note that due to societal norms the male head of household is usually the owner (even if women financially contributed in building the house). However, the programme supported a total of 595 Palestinian women displaced during the 2014 Gaza Conflict to receive legal counselling and/or representation.

Summary of responses to issues raised in previous annual reviews (where relevant)

The Annual Review from April 2016 recommended that DFID and NRC should review the ongoing need to support Palestinian women who were displaced through the 2014 Gaza Conflict and agree appropriate targets for the next six months. The target for this indicator was changed to reflect NRC’s work during the last six month of the programme. However, the new target was slightly underachieved.

Recommendations for future programmes

For future programming, it is recommended that NRC explores altering this indicator so as to reflect the context in Gaza as more and more households (including women-headed households) are accessing reconstruction grants and there is good progress on the overall Gaza reconstruction mechanism. It is also recommended that future programming could be expanded into a broader assessment of women’s needs in relation to HLP rights/legal aid.

Output Title	Preventative Legal Response - A longer term legal strategy that helps to prevent demolitions and displacement
Output number per LF		2	Output Score (for period 1 April 2016 – 30 September 2016)	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones / Six months to September, 2016	Progress / Six months to September, 2016	Total Target	Total Achieved
2.1	Number of people receiving HLP and residency training or technical assistance from NRC (sex disaggregated)	275 total comprising: / West Bank: 175 (125m/50f) / Gaza: 100 (50m/50f)	279 total comprising: / West Bank: 173 (124m/49f) / Gaza: 106 (63/743f)	3,125	3,684
2.2	Number of instances where beneficiaries of training or technical assistance have used information received from NRC training and technical assistance in their work.	This indicator is no longer tracked as an output; instead we monitor the feedback as an outcome indicator.	N/A - Outcome Indicator	N/A	N/A
2.3	Number of people receiving information services (sex disaggregated)	Total 775 comprising: / West Bank: 275 (200m/75f) / Gaza: 500 (250m/250f)	Total 801 comprising: / West Bank: 297 (157m/140f) / Gaza: 504 (128m/376f)	Total: / 13,095	Total: / 13,265 / Males: / 5,024 / Females: / 8,241

Key Points

Output Indicator 2.1 Technical Support and Training: NRC provided training sessions for a total of 279 individuals (both males and females) on HLP and thus slightly exceeded the target for the six month reporting period. In total, the programme reached 3,684 individuals with training and/or technical assistance. The sessions covered amongst other topics the applicability of international humanitarian law to the OPTs; the planning and permit regime in Area C; and HLP rights. Meanwhile in Gaza, HLP trainings were undertaken targeting legal practitioners, law students and Mukhtars (tribal chiefs). Trainees’ knowledge and capacity were improved. 95% of trainees have reported using the knowledge gained from the training sessions during preparation of written documents or briefs, legal reports, provision of legal advice or casework, conduction of legal research, provision of advice on field work and in project planning/implementation.

Output Indicator 2.3 Information Sessions: In the West Bank, there was a high need for information on issues related to house demolitions, and restrictions on movement, - which is reflected in the increased number of beneficiaries (801) attending information sessions. Whereas in Gaza, the ICLA team provided information sessions to increase participants’ awareness about their HLP rights. Feedback from beneficiaries has identified how essential knowledge in HLP has become in Gaza, particularly following the 2014 conflict. In total, the programme reached 13,265 individuals with information services.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no recommendations specific to output 2 in the last Annual Review.

Recommendations for future programmes

For future programmes, it is recommended that information sessions should be targeted to respond to the different needs of the different groups, and feedback from beneficiaries on the use of training sessions would be a better indicator to measure the benefits of such information sessions.

Output Title	Policy Change Response: Influencing policy change on HLP and residency rights violations through advocacy.
Output number per LF		3	Output Score (for period 1 April 2016 – 30 September 2016)	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones / Six months to September, 2016	Progress / Six months to September, 2016	Total Target	Total Achieved
3.1	Number of advocacy briefings given on specific housing, land, property and residency issues (verbal or written).	20	29	290	419
3.2	Number of research documents prepared on identified HLP and residency issues. .	4 / (2 West Bank, 2 Gaza)	4 / (4 West Bank and 0 Gaza). [7]	54	57
3.3	Number of discriminatory and/or unfair laws, policies or practices exposed through public interest cases.	3 cases	29 cases	78	152
[7] The documents were translated into Arabic and we used them in the information sessions targeting communities as well as schools, also used in the NRC Symposiym and in donor breifings.

Key Points
Output 3.1 Advocacy Briefings: 29 verbal and written advocacy briefings were given on specific HLP issues related to the West Bank and Gaza, therefore overachieving the agreed milestone for the six month reporting period; bringing the total number of verbal and written briefings to 419. In the West Bank, NRC has been particularly active in attempting to counter the ongoing demolitions of Palestinian homes and infrastructure, through advocating for HLP rights, and in providing advocacy support to public interest cases, through numerous meetings and briefings in Jerusalem, Tel Aviv and Brussels. The project successfully encouraged the understanding and use of IHL language by States and the UN in relation to prevalent violations in the West Bank and Gaza.

Output 3.2 Research: In total, 57 research documents were prepared on issues related to Housing, Land and Property rights and residency issues.

Output 3.3 Public Interest Cases: NRC and partners worked on 29 public interest cases challenging unjust HLP and residency issues during the six month reporting period bringing the total number of public interest cases to 152. The full list of cases for the reporting period is detailed in annex 2.

Summary of responses to issues raised in previous annual reviews (where relevant)
The last Annual Review recommended that NRC should look to engage further with missions based in Jerusalem, Ramallah and Tel Aviv to assess how materials are being used by the international community and shape their future advocacy strategy given the increase in demolitions. This should include making advocacy materials more widely available in Arabic for beneficiary communities. [8]
[8] All factsheet documents were translated into Arabic.

Recommendations for future programmes
NRC should assess what advocacy approaches have worked and build on those to inform future advocacy strategies.

Output Title	PA Capacity Building Response: Strengthen the capacity of the PA to provide legal aid in HLP cases.
Output number per LF		4	Output Score (for period 1 April 2016 – 30 September 2016)	A++
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones / Six months to September, 2016	Progress / Six months to September, 2016	Total Target	Total Achieved
4.1	Number of technical services provided to the PA to strengthen their capacity.	5 technical services	33 technical services	22	94
4.2	Number of direct issues of cooperation where NRC is actively working with UNDP and PA and legal aid partners on development of a sustainable legal aid system for housing, land and property law	5 direct issues	33 direct issues	23	87

Key Points

Output Indicator 4.1 Technical Services: During the six month reporting period, there were 33 technical services provided to the Palestinian Authority and therefore this target substantially exceeded the agreed milestone. This brought the total number of technical services provided to 94. Technical services included:

- Provision of technical services to the PA and legal practitioners on 14 accounts in the form of Geographical Information System mapping and legal correspondence with Israeli governmental institutions for Public Interest and individual cases.
- Provision of technical assistance in the form of follow-up with beneficiaries in Hebron H2.
- Mobilisation of the PA to take actions aimed at curbing settlement expansion and coordinated cases referral and information sharing and gathering in relation to new and ongoing cases adopted by the Anti Wall and Settlement Commission lawyers.

Output Indicator 4.2 Issues of Cooperation: There have been 33 issues of cooperation which represent substantive legal cases not minor coordination events or meetings. This target was substantially overachieved for the six month reporting period. The aim of this cooperation is to provide the PA with resources for more systematic and institutionalised knowledge of cases and with the ability to analyse trends to allow strategic policy decisions related to legal aid delivery on HLP issues. The total number of direct issues of cooperation with the PA is 87.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no recommendations specific to output 4 in the last Annual Review.

Recommendations for future programmes

N/A.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers of this project were grants to partners, lawyers’ fees and staff salaries. The value for money of the grants to partners and lawyers’ fees was measured principally by the number of cases dealt with, but also by the positive impact of this legal work on the lives of Palestinians. Fees were paid to private lawyers, partner Civil Society Organisations (CSOs) employing in-house lawyers and other legal consultants.

There was a need to strike a balance between low legal fees and the provision of high quality legal services. Payment of low fees may have resulted in poor quality legal work, thus compromising the goal of ensuring access to justice and fair trial standards. The situation was particularly challenging in the OPTs on account of the complexity of cases, the need for specialists in certain areas of the law (including housing, land and property law), the need for either Hebrew speaking (Area C) or Israeli-bar qualified lawyers and the limited pool of available lawyers. Some beneficiary communities also showed a strong preference for private lawyers. Many of the public interest cases funded by the NRC required a high level of legal expertise and a remuneration rate sufficient to attract quality lawyers.

VfM performance compared to the original VfM proposition in the business case

Economy: NRC developed and implemented a legal aid fee structure for private lawyers. It considered the advantages and disadvantages of working with private lawyers, using a mixed approach to ensure high quality legal representation and additional capacity to take on cases to supplement the role of CSOs. NRC maintained a Table of Fees for legal procedures used to evaluate the cost for each legal case.  The Table of Fees was developed by the ICLA programme in 2013 following market research into fees charged by legal practitioners in the West Bank (Area C) and factoring in a ‘legal aid’ discounted rate.  The Table was designed to balance consistency and cost-effectiveness in legal fees and services and was reviewed periodically. The Table was consistent with the NRC approach internationally and EU rules.

Efficiency: The residency cost extension (approved in 2014) provided particularly good value for money since it used the existing ICLA structure, coordination and advocacy resources and so kept support costs low while programme activity expenditure was high. The efficiency of the programme improved significantly over the last year as NRC have greatly reduced consultancy fees for research reports though doing more of this work in-house, except where specific expertise was needed.

Cost effectiveness: NRC nationalised one international position during the review period and used the funding gain for additional programme activities. In 2014, NRC finalised a research study into the cost of displacement which found that the total cost incurred per household displaced in Area C is over £100,000. Our original business case estimates that it costs some £4,700 per case to provide legal advice to prevent demolitions and evictions. This figure has not significantly changed over time. It was therefore still far more cost effective to prevent displacement through providing legal assistance than to provide compensation or humanitarian aid after displacement has occurred.

The fact that programme did not always employ the cheapest legal services, but services were consitently shown to be high quality through the positive outcomes achieved.

Over the period 2013-2016 an estimated £1,445,142 was spent directly on legal cases which challenged demolitions or evictions. 2,541 eviction or demolition orders were suspended as a result. The average household impacted by displacement was analysed to suffer economic damage worth NIS680, 648 ($185,362).[9] Averting 2,541 evictions/demolition orders can therefore be estimated to be worth 2,541 x $185,362 = $471,004,842 (£330,427,686). The benefit/cost ratio is £330,427,686/£1,445,142. In other words, every £1 spent returns £228.60 in benefits. This is a good rate of return.
[9] This is comprised of a number of factors, including loss of property (house and/or land owned by the household), loss of productivity due to worsened living conditions and legal fees and fines levied by the Israeli courts. Shir Hever (2015) The Economic Impact of Displacement

Assessment of whether the programme continues to represent value for money

According to the measures outlined above, we deem that the programme represented good value for money. It is worth mentioning that when cost extensions were approved (summarised on page 1), log frame targets were amended in line with the Value for Money assessment.

The residency work provided good value for money as a large number of legal issues for beneficiaries were resolved through a one-off counselling session. Such counselling was relatively inexpensive, compared to full case representation.

Quality of financial management during programme

NRC’s financial forecasting has been strong over the reporting period, with less than 10% variance between forecast and expenditure for four out of the four quarters.

Date of last narrative financial report	01/11/2016
Date of last audited annual statement	31/12/2015

E: RISK (½ page)

Quality of risk management over the life of the programme

NRC had effective risk mitigation and management procedures in place and demonstrated effective use of these throughout the programme. NRC had in place a robust mechanism to identify their implementing partners and assess the degree to which they would require NRC’s support to implement the programme. This resulted in either NRC delegating implementation entirely, or only delegating limited decision making powers to the partner organisation. This mixed model was adopted when the partner had limited management, programmatic or organisational capacity and NRC wanted to retain control to better identify and manage risks. Afterwards, NRC applied the ‘local partner risk assessment tool’ to enable NRC decision makers to assess whether a potential partner poses a financial, reputational and programmatic risk to NRC operations and a protection risk for beneficiaries. The tool was designed to help qualify and quantify the risk and to determine the appropriate mitigation strategies, where possible.

In the event of any potential risks, NRC consistently warned DFID and the other donors as soon as possible to flag any unforeseen risks. The NRC team regularly informed donors and other related stakeholders of the risk and challenges it faced, the potential impact of these and the steps it would be taking to mitigate these.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

As outlined above, NRC delivered according to the agreed targets, overachieving against many target indicators.

Performance of partnership (s)
We maintained regular contact with NRC both in one to one meetings, co-ordination forums and during field visits and briefings which they regularly organised for DFID and FCO high level visitors or new staff. NRC provided us with narrative and financial reports on time and in line with the agreed schedule.

The Donor Coordination Meetings that were initiated in 2012 have been continued through the reporting period (during the past six months, one donor co-ordination meeting took place). These meetings brought NRC’s donors together to discuss current challenges, contextual changes, and future direction and to coordinate on advocacy initiatives. The meetings were useful to increase donor co-ordination and communication, but they did not significantly reduce NRC’s administrative burden.

Asset disposal and value obtained by DFID
This programme did not fund major assets, but rather NRC’s ongoing activities principally through paying lawyers’ fees, providing grants to partner NGOs and staff salaries. However, DFID paid for office stationery and equipment. NRC used to send updated asset lists every 3 months; however after programme closure, the assets will be transferred to NRC to be utilised in the new FCO programme, as this option demonstrates the best value for money and ensures that the assets will be put to a good developmental purpose and this also contributes to strengthening the one HMG approach.

G: CONDITIONALITY (½ page)

Partnership principles assessment
The partnership principles are not relevant in managing and monitoring the programme, although NRC’s work helped to reduce poverty, achieve land and livelihoods-related MDGs, and promote respect for human rights and international law. As outlined in Output 4 above, NRC supported the technical capacity of the Palestinian Authority (PA) for which DFID has a Partnership Principle Assessment. DFID OPTs carried out quarterly assessments against the partnership principles as part of our disbursements to the State Building and Service Delivery Grant.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
We were able to monitor the impact of NRC’s work through regular field visits, which NRC organised in order to brief the international community about the challenges facing Palestinian communities (particularly Bedouin and herding communities) that are vulnerable to demolitions, displacement and violations of residency rights.

Many of the activities funded – the provision of legal aid, training etc. - were carried out by downstream partners who have direct agreements with NRC. It is therefore not possible for DFID to directly monitor all aspects of NRC’s work, although NRC works very closely with partners to ensure effective delivery of results.

Several NRC internal evaluations were carried out of different aspects of this NRC programme in other countries during 2013 and 2014.

Monitoring progress throughout the review period
In addition to this programme review process which was carried out in close communication with the manager of NRC’s ICLA project, NRC provided narrative updates against indicators every six months which allowed us to monitor whether they were on track to meet results targets. They also contributed updated data twice a year to the DFID Results Framework and Operational Plan results that were collected and analysed centrally.

As mentioned above, NRC regularly organised field trips for diplomatic missions and high level visitors, including from the British Government, to vulnerable communities, providing us with many opportunities to meet with the beneficiaries of NRC’s work and monitor progress.
Annex 1: Overall Output Progress 2013/14 to 2016/17 (1 April 2013 – 30 September 2016)

The below table provides an overview of output indicators’ progress against the baseline set in 2013:
Emergency Legal Response		Baseline 2012	2014		2015	March 2016 / (12-month results)	September / 2016 / (6-month results)	Total / 2014 to 2016
1.1 # Of male and female beneficiaries receiving legal counselling on HLP and residency issues. [10]		1,240	2,296		3,778	1,078	496	7,648
1.2 # Of Opened and ongoing cases of legal assistance.		405	264		781	1,236	1,734	4,015
1.3 # of Palestinian women displaced during operation Protective Edge in Gaza who receive legal counselling and/or representation from NRC or NRC partners.		200	34		421	100	40	595
Preventive Legal Response
Indicator	Baseline 2012		2014		2015	March 2016 / (12-month results)	September / 2016 / (6-month results)	Total / 2014 to 2016
2.1 Number of people receiving HLP and residency training or technical assistance from NRC (sex disaggregated)	455		1,046		1,667	692	279	3,684
2.2 Number of instances where beneficiaries of training or technical assistance have used information received from NRC training and technical assistance in their work.	15		53		139	N/A / Outcome Indicator	62	N/A / Indicator was measured as an outcome indicator.
2.3 Number of people receiving information services (sex disaggregated)	2,035 / 575 / Males / 1,460 Females		4,169 / 1,394 Males / 2,775 / Females		6,470 / 2447 / Males / 4,023 / Females	1,851 / 898 / Males / 953 / Females	801 / 285 / Males / 516 / Females	13,265 / Males: / 5,024 / Females: / 8,241
Policy Change Response
Indicator		Baseline 2012	2014		2015	March 2016 / (12-month results)	September / 2016 / (6-month results)	Total / 2014 to 2016
3.1 Number of advocacy briefings given on specific housing, land, property and residency issues (verbal or written).		60	95		155	140	29	419
3.2 Number of research documents prepared on identified HLP and residency issues. .		10	18		25	10	4	57
3.3 Number of discriminatory and/or unfair laws, policies or practices exposed through public interest cases.		15	37		57	29	29	152
Palestinian Authority Capacity Building Response
Indicator		Baseline 2013		2014	2015	March 2016 / (12-month results)	September / 2016 / (6-month results)	Total / 2014 to 2016
Number of technical services provided to the PA to strengthen their capacity.		0		5	11	45	33	94
Number of direct issues of cooperation where NRC is actively working with UNDP and PA and legal aid partners on development of a sustainable legal aid system for housing, land and property law.		0		3	6	45	33	87
[10] This indicator was changed during the course of the programme.

Annex 2: List of Public Interest Cases in Area C

1. Abu Nuwar Case
2. Masafer Yatta Demolitions
3. Sa’ir
4. Atta Jaber
5. Military Order 418
6. Cremisan Convent & School
7. Beit Al Baraka
8. Abu Rajab
9. Hebron Gold Market
10. Hebron Jewish Cemetery Area
11. Al Ras Land